What I did, and what I’m doing

One timeline, February to October 2026, for reading on the train

Written 28 October 2026. About 15 minutes to read.

The whole thing in two paragraphs When many AI agents share something limited, some take more than their share. An overseer can only afford to check a few of them. When does checking a few agents stop the cheating, and how should the overseer choose whom to check and how hard to punish? I spent February to September building games and comparing ways of governing them. In October I narrowed it to audits and penalties, and found that the penalty that stops an LLM agent can be predicted by watching it first. Now I’m moving the work into a standard multi-agent RL game, SocialJax Harvest, with learning agents and very few checks.

# 1. The timeline at a glance

| When | What I did | What came out of it |
| --- | --- | --- |
| Feb | Built Fishery: a fish stock that regrows. Weak strategies were replaced by new ones, so better ones could “invade”. | A working game. No result yet. |
| Mar | Added Harvest: patches of apples, neighbours affecting each other. Local vs system-wide fixes, and a quick RL (PPO) check. | A wider comparison, but small, setting-dependent differences. |
| Apr | Gave the monitor real limits: it misses things, it’s slow, checking costs. Built tools for LLM-written strategies. | More realistic, but too many things changed at once. |
| Jun | Stage A: local checks vs whole-system checks, ranked on a “capability gap” axis. | The axis turned out to be invalid and was withdrawn. |
| Sep | A fair reviewer test (same powers, different information). A budgeted reviewer. A SocialJax Clean Up attempt. | The fair test worked. Clean Up gave no usable test. |
| 5 Oct | Audit of the September result. | A bug (a weather buffer 3.6× too big) had produced most of it. |
| 5–9 Oct | Scripted cheaters vs audits, fines and memory, in Fishery, Forest and River. | Penalties must be real; the stopping point can be predicted; several designs backfire. |
| 6–8 Oct | LLM fishers (4 models, 400+ games). Stopping penalty predicted before testing. | It held for the two models that cheat. |
| 12–13 Oct | L4, L5, L6 started: new games, more models, cheating spreading. | The prediction held again. Announcing a zero fine made cheating worse. |
| 13 Oct | Catch-up meeting with slides. | Feedback: the cost of monitoring, talking and contagion, welfare, a success metric, an LLM overseer, a real 2D game. |
| 13–14 Oct | Read 58 AI papers. Studied how 93 sources build their games. | Decision: build the overseer as a plug-in, and put it into existing games. |
| 14 Oct | Phase 0 checks: is each game really a dilemma, and do the results survive changes to the settings? | Mostly yes. Forest isn’t a real dilemma. A lone cheater needs about 3× the penalty. |
| 14 Oct | Built the overseer plug-in. | It replays every stored game exactly. |
| 14–19 Oct | R1a: audits on Richard’s code, 64 agents. | Selfish takeover reversed. Welfare 0.13 → 0.87. |
| 19–20 Oct | R1b: LLM strategies told the audit rule. | They comply but stay selfish: “compliance is not conversion”. |
| 23–27 Oct | OpenMined grant draft. A PhD plan. Workshop paper paused. | Plan: an overseer that calibrates itself. |
| 28 Oct | Reframed into multi-agent RL, with SocialJax first. | This document. |

# 2. Act 1: February to September — governing a commons

The idea at the time: commons games, where agents share a resource that regrows, are the standard way to study cooperation in multi-agent RL. I wanted to compare ways of governing them.

## What I did

- Fishery (Feb): one shared fish stock. Strategies that did badly were replaced by new ones, so better ones could invade (hence the repo name, “invasion commons”). I added quotas, monitoring and sanctions.

- Harvest (Mar): a map of apple patches where neighbours affect each other. This lets you separate what one agent sees from what happens to the whole map.

- Monitor limits (Apr): at Yali’s request, the monitor got real limits: it misses things, it’s slow, and checking costs.

- Stage A (Jun): each request can look fine while the combination breaks the system. I ranked overseers on a “capability gap” axis.

- Fair test (Sep): two reviewers with the same powers, differing only in what they can see, plus a reviewer that can check only 0, 3 or 6 requests. Then 1,920 fresh games to confirm.

- SocialJax Clean Up (Sep): I built an adapter, but the strategies I picked never created situations worth judging.

## What I read

Ostrom 1990 (communities managing commons); Leibo et al. 2017 (social dilemmas over time); Perolat et al. 2017 (RL agents harvesting a resource); Melting Pot; SocialJax; GovSim (LLMs emptying a fish lake); Bowman 2022 (scalable oversight); Makins et al. 2026 and Hu & Wang 2026 (monitoring many agents).

## Honest verdict

- The question kept moving. Too many things changed at once, so few results point to one cause.

- The capability axis was one rank minus another. It wasn’t a real measurement, and I withdrew it.

- “Each request looks fine, but together they break it” was already known in the literature.

- A bug produced most of the September headline (found 5 October).

- But it was in the right field: multi-agent RL, Harvest, PPO, SocialJax. Yali’s questions then are still the right ones: what problem are we solving, and who are the players?

# 3. Act 2: 5–13 October — audits and penalties

The idea: stop comparing everything and ask one question. When do a few random checks stop agents taking more than their share?

## Scripted agents (5–9 October)

- Checks that only fix the current decision barely help. Checks need a consequence.

- Memory (cutting a caught cheater’s future share) cut harm in 12 of 12 settings across three games.

- Cheaters stopped where predicted: in 5 of 5 new settings, within one step.

- Things that backfired:

  - a known audit schedule (worse than no audits);

  - cutting everyone’s share to absorb cheaters (cheaters gained more than with no audits: 142 vs 113);

  - always checking the biggest agent (caught 25% of liars vs 100% at random).

## LLM agents (6–13 October)

- Four of the six fishers were language models: gpt-oss, Nemotron, Gemma and Mistral.

- A model only cheated when told it was allowed to.

- I watched each model with no penalty, measured how much it grabbed when it cheated, and wrote down a prediction: a penalty of 30 should stop it.

- Nemotron stopped exactly at 30; gpt-oss one step early, at 24. This held again on new games (L4).

- They respond to what they grab this round, not to what cheating costs them over the whole game.

- Announcing checks with a zero penalty made cheating worse: 58% of rounds vs 30% when checks were never mentioned.

- Gemma barely cheated and Mistral never did, so neither can tell me anything about penalties.

## What I read

Greenblatt et al. 2024, “AI Control” (checking ~2% of an AI’s work; safety vs usefulness; a red team), read in full. Becker 1968 (the break-even rule), metadata only. Inspection games. Okamoto et al. 2026 (stating a penalty turns a rule into a price). Gneezy & Rustichini 2000 (“A fine is a price”).

## Honest verdict

- Strong: the LLM penalty was predicted before testing and held on new games. The backfire findings are real. Every protocol was frozen before its code.

- Weak: much of the scripted work is true by design, since those bots were built to stop at break-even.

- Weak: the LLMs were told the odds and the penalty, so they may just be doing sums.

- Weak: only 2 models cheat, there are 10 games per condition, and it’s one home-made text game.

- Weak: checks covered 9–34% of actions, not the ~2% that AI safety assumes. There were no learning agents.

- Weak: the framing drifted from multi-agent RL to economics. That’s the loop I’ve been feeling.

# 4. The 13 October meeting

I presented Act 2. The questions back were:

- Cost of monitoring: checking isn’t free, so account for it.

- Communication and contagion: what if an agent sees another cheat and copies it? How should the overseer react? Ground it in Richard and Janny’s paper.

- Individual vs group welfare, and how to choose a good environment.

- A metric that shows the overseer works.

- An LLM as the overseer.

I added two of my own: make it a real 2D game like SocialJax, and read more AI papers, fewer economics papers.

# 5. Act 3: 13–28 October — after the meeting

## Reading and deciding (13–14 October)

- 58 AI papers checked. The closest work is LLM enforcement studies (peer reports, voted restitution, stated penalties). None varies how often agents are checked, or predicts the stopping penalty.

- How games are built (93 sources): every platform picks its numbers by hand, then checks that the game is a real dilemma and that results survive changes to the settings.

- Decision: build the overseer as a plug-in that works on any game, and use existing games rather than building my own.

## Phase 0: checking my own games (14 October, free)

- All three games are real dilemmas without the overseer. Results survive changes to the settings in 19 of 20 cases.

- Forest isn’t a real dilemma once the overseer is in place: the damage hits the forest, not the agents’ scores. Still to decide what to do with it.

- A lone cheater needs about 3× the penalty that a group of cheaters needs.

- Cost of monitoring (meeting point 1): checks are worth it only if each one costs less than 0.03–0.24 t of fish.

- Being caught didn’t change what an LLM did next round, and cheating jumped at the end of the game.

## The overseer plug-in (14 October)

One piece of code that sets allowances, picks whom to check, and applies penalties or memory in any game. It replays every stored LLM game exactly.

## R1a: audits on Richard’s code (14–19 October, free on GitHub)

- Willis, Zhao, Du & Leibo 2026: hundreds of LLM agents write strategies as code, and the strategies that earn more get copied. With 64 agents per group, selfish strategies take over.

- I added random checks and penalties, with the penalty level predicted before running.

- Result: cooperative strategies went from 15% to 60% just above the predicted penalty, and to 84% at double it. Welfare went from 0.13 to 0.87. Rare checks with big penalties were cheaper than frequent small ones.

## R1b: what if the strategies know the rule? (19–20 October, about $0.58)

- Selfish strategies cut cheating from 74% to 6%. Three in four wrote “chance × penalty vs gain” straight into their code.

- Compliance is not conversion. Selfish strategies survived (only 19% were cooperative) but behaved well enough that welfare reached 0.45, vs 0.13 without that knowledge. Remove the checks and they cheat again.

- This answers meeting point 4: judge the overseer by behaviour and welfare, not by how many “good” agents there are.

## Other things

- L5: DeepSeek cheated in 80% of rounds and emptied the lake in 10 of 10 games. Testing its predicted penalty would cost ~$11, so it’s untested. GLM was too expensive.

- OpenMined grant drafted. It closes 30 October.

- 27 October: workshop paper paused; PhD plan written (an overseer that calibrates itself).

- 28 October: I decided to stop leaning on economics. The work is now framed in multi-agent RL.

# 6. What I can and can’t claim

| I can say | I can’t say yet |
| --- | --- |
| The penalty that stops an LLM agent can be predicted by watching it first (2 models). | That it works in a real grid game like Harvest. |
| LLMs respond to this round’s gain, not the whole game’s. | That it works against RL agents that learn to dodge it. |
| It works at 64-agent scale on someone else’s code. | That it works with very few checks (~1–5%). |
| Several sensible-sounding designs backfire. | That it works when agents aren’t told the odds. |
| Oversight makes agents comply, not change. | Why the models stop, or anything about people. |

# 7. Where I’m going now

The question, in multi-agent RL terms In SocialJax Harvest, an overseer can check only a few agents each step. Whom should it check and what should it do, so that learning agents keep the orchard alive at the lowest checking cost? Multi-agent RL already has fixes for the commons: agents that care about fairness, agents that punish or pay each other, a planner that taxes everyone. In the papers I read, the fixer sees every agent at every step. Mine can only check a few.

## The gameplan

- One page with Yali: the question and the players. Agree it before any code. This is what Act 1 skipped.

- Define “cheating” in Harvest, for example taking an apple from a nearly empty patch, so the patch can’t regrow. Check that scripted bots produce both cheaters and non-cheaters, and that the game is still a dilemma. This is where Clean Up failed in September.

- Put the overseer into SocialJax Harvest as a wrapper and test it with scripted bots. Free.

- Train RL agents against it. Compare no overseer, one that sees everyone, one with only a few checks, and agents zapping each other. Small on CPU first, then CREATE.

- Make it set itself up: watch first, set the penalty, keep checking and adjust.

- Let learning agents try to beat it. They’ll learn to cheat where it isn’t looking, which makes them a ready-made red team.

- LLM players and an LLM overseer in OpenSocialJax, kept small for credit.

- Talking and copying: does cheating spread, and can the overseer react? (Meeting point 2.)

The October work becomes the pilot study. Its lessons are the overseer’s design rules: check at random, punish the cheater not everyone, make consequences real, and measure behaviour.

# 8. Decisions waiting on me

- OpenMined grant: submit or not, by 30 October.

- CREATE / GPU: ask Yali for access. I don’t know whether the 14 October message was sent.

- Forest: move it to the supplement (recommended).

- Credit: about $9 left on Ollama. Don’t spend it on the text games.

# 9. To remember

## Three ideas

- Watch first, then set the penalty. It predicted where LLMs stop.

- Some obvious designs backfire: announcing checks with no penalty, punishing everyone, always checking the biggest agent.

- Watched agents behave; they don’t change.

## Five numbers

| Number | Meaning |
| --- | --- |
| 30 | the predicted stopping penalty; Nemotron stopped exactly there |
| 58% vs 30% | cheating with checks announced at zero penalty vs never mentioned |
| 25% vs 100% | liars caught by always checking the biggest agent vs checking at random |
| 0.13 → 0.87 | welfare in Richard’s 64-agent game, without vs with the overseer |
| 19% / 0.45 | only 19% of strategies were cooperative, but welfare still reached 0.45: they comply without changing |

Details: notes/phd_plan/what_we_did_before_13oct.md and talking_about_my_work.md in the repo.